**ESSER III Grant**

**Uses of Funds Plan**

**Nursery ISD**

**2021-2024**

**Addressing the Instruction/Academic Loss of Time**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Instructional Activities** | **ESSER****Application Activity** | **Person Responsible** | **Amount of ESSER****Funds** | **Timeline** | **Formative Evaluation** |
| Obtain a Math Interventionist for K-5th.Summer Reading ProgramSummer School/Tutoring Reading Resources  | A1, A16, A6 | Superintendent Special Programs/Ast. Principal | $ 55,000 (X3) | 2021-20222022-20232023-2024 | Attendance RostersBOY, MOY, EOY Assessments, STAAR / EOY performance, POs for Reading Resources |
| Provide Summer Dyslexia Services and Ongoing to exit students prior to leaving NISD in 5th Grade. | A2 | Superintendent Special Programs/Ast. PrincipalDyslexia Teacher | $3,500 (X1) | 2021-20222022-20232023-2024 | Attendance Records, End of 5th Grade Exit percentage.  |
| Organizational Efficacy: PD Science of Teaching Reading, Reading Academies, MTSS | A7 | Superintendent | $ 50,000 (x1) | 2021-20222022-20232023-2024 | RTI/MTSS Documentation, Teacher Completion of SoTR/RA, Student Growth Logs in BOY, MOY, and EOY.  |
| Sanitation of Facilities  | A9 | M&O, Superintendent | $7500 (x3) | 2021-20222022-20232023-2024 | COVID-19 Expenses on Sanitation Solution, Clear Student Barriers, Attendance Records |

**Social/Emotional and Behavioral Issues**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Instructional Activities** | **ESSER****Application Activity** | **Person Responsible** | **Amount of ESSER****Funds** | **Timeline** | **Formative Evaluation** |
| Obtain and Retain a full time counselor for Social Emotional Learning and Behavior Support Activities (split funded) | A6, A7, A15 | Superintendent | $10,000 (x3) | 2021-20222022-20232023-2024 | Weekly whole group class lessons, counseling logs, Discipline Records, BOY, MOY, and EOY progress measure.  |

**Technology**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Instructional Activities** | **ESSER****Application Activity** | **Person Responsible** | **Amount of ESSER****Funds** | **Timeline** | **Formative Evaluation** |
| Technology to Support Online Learning and At Risk Students | A17 | Superintendent  | $ 5000 (x3) | 2021 - 20222022 - 20232023 - 2024 | POs for Hotspots, Chrombooks, Servers, and other technology to support student learning loss or student learning, BOY, MOY, and EOY Student Growth Measure |

**Family Engagement**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Instructional Activities** | **ESSER****Application Activity** | **Person Responsible** | **Amount of ESSER****Funds** | **Timeline** | **Formative Evaluation** |
| Attendance Support | A13, B4 | Superintendent Counselor | $500 (x3) | 2021-20222022-20232023-2024 | Distribution of attendance support prizes/ awards/ certificates.Documentation of student absence percentages.Student Awards and Ceremonies  |

**Maintenance and Operations/Facility**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Instructional Activities** | **ESSER****Application Activity** | **Person Responsible** | **Amount of ESSER****Funds** | **Timeline** | **Formative Evaluation** |
| Sanitation of Facilities  | A9, B5, B6, B7, and B9 | M&O, Superintendent | $7500 (x3) | 2021-20222022-20232023-2024 | COVID-19 Expenses on Sanitation Solution, Clear Student Barriers, Attendance Records |